Q3 Office Move Plan

Summary

Move the practice Seattle team to the fourth floor. The draft must explain why the move is proposed, what it costs and who owns each decision.

Timeline

Week 1 – Packing

Label equipment, confirm inventory and back up local work.

Week 2 – Move day

Move the team in two groups and check network access.

Week 3 – Setup

Resolve missing items, review accessibility and collect feedback.

Responsibilities

Dana coordinates the practice plan. Marcus checks vendor options. Priya reviews the onboarding guide. These are invented roles for the lesson.

Budget

Compare monthly printer leases:

Northline Print: £145; setup 3 days.

ClearCopy: £129; setup 5 days.

Brightway Imaging: £160; setup 2 days.

PaperTrail Ltd: £138; setup 4 days.

Exercise addition: Kestrel Office Supply: £152; setup 1 day.

Keep GBP costs separate from any USD examples; no currency conversion is supplied.

Risks

Network downtime

Network downtime may delay the first morning.

Furniture delays

Furniture delays may leave some desks incomplete.

Label all additional estimates as your assumptions.